## Frontend Unity
Feature | Description | Unity Implementation | Priority | Phase | Timeline | Dependencies | Notes
App Logic Editor | Visual editor for VR app logic: Sub-elements include state machine UI (drag-drop states), event triggers (onInput/onEvent), cross-platform input mappings (Oculus/SteamVR), scriptable logic templates, and error checking for state conflicts. Workflow: Create state → link events → test on platform. Metrics: <1s state transition. | XR Interaction Toolkit v2.5; Unity Visual Scripting for states; OpenXR input mappings. | High | Phase 1 | Dec 2025 | Custom Asset Library, Scene Service | Core for app devs; test Quest 3/SteamVR; edge cases: input conflicts; effort: 30 person-days.
Multi-Platform Build Tools | Build VR apps for Quest/PC/WebXR: Sub-elements include build config UI (APK/EXE/WebGL), automated SDK injection (Oculus/SteamVR), platform-specific optimizations (e.g., Quest LODs), build validation, and error logs. Workflow: Select platform → configure → build. Metrics: <5min build. | Unity Build Pipeline; custom SDK scripts; Unity Cloud Build. | High | Phase 1 | Dec 2025 | Publishing Service | Edge cases: SDK version mismatches; effort: 35 person-days.
Interactable System | App interactions: Sub-elements include haptic feedback (variable intensity), multi-object grab for app controls, platform-specific input bindings, event triggers for app logic, and voice input support. Workflow: Assign interaction → test on platform → save. Metrics: <10ms haptic latency. | XRGrabInteractable; OpenXR haptics; custom UnityEvent system. | High | Phase 1 | Dec 2025 | Scene Service | Test on Quest/Vive; edge cases: multi-platform input; effort: 25 person-days.
Animation for Apps | App animations: Sub-elements include keyframe UI for UI transitions, skeletal rigging for characters, blend shapes for app states, VR preview for animations, and export to platform formats (GLTF/USD). Workflow: Create animation → test → export. Metrics: <1s export. | Unity Timeline v1.8; Mixamo; custom VR UI. | High | Phase 2 | Mar 2026 | Asset Service | Edge cases: platform-specific playback; effort: 30 person-days.
Physics for Apps | App physics: Sub-elements include rigidbody for interactive controls, soft-body for UI effects, collision events for app logic, raycasting for selections, and platform-optimized physics. Workflow: Add physics → configure → test. Metrics: <5% CPU. | Unity Physics (DOTS); NVIDIA PhysX 5.0. | High | Phase 2 | Mar 2026 | Scene Service | Optimize for Quest; edge cases: high-velocity; effort: 30 person-days.
Visual Scripting for Apps | No-code app logic: Sub-elements include node-based UI for app flows, VR event nodes (onInput/onStateChange), debugging tools, templates for app patterns (menus, inventory), and exportable scripts. Workflow: Create nodes → test → deploy. Metrics: <1s execution. | Unity Visual Scripting v1.8; custom VR nodes. | High | Phase 1 | Dec 2025 | None | Edge cases: cyclic graphs; effort: 20 person-days.
App Rendering | Cross-platform rendering: Sub-elements include URP/HDRP toggles, platform-specific shaders (Quest/PC), light baking for apps, volumetric effects for UI, and adaptive quality. Workflow: Configure render → test platform → optimize. Metrics: 90 FPS. | URP v14; Bakery plugin; custom VR shaders. | High | Phase 1 | Dec 2025 | None | Edge cases: mobile performance; effort: 25 person-days.
Input Configurator | Platform input mappings: Sub-elements include gesture recognition (pinch/swipe), controller bindings (Oculus/SteamVR), keyboard/gamepad support, input remapping UI, and calibration tools. Workflow: Map input → test → save. Metrics: >95% accuracy. | OpenXR 1.9; Oculus Integration v50. | High | Phase 2 | Mar 2026 | Interactable System | Edge cases: input conflicts; effort: 20 person-days.
Custom Asset Library | App asset management: Sub-elements include async uploads, AI-suggested tags, thumbnail generation, sharing permissions (public/team), versioning, moderation tools, and drag-drop to app projects. Workflow: Upload asset → tag → use in app. Metrics: <2s thumbnail. | Custom UI; AssetDatabase caching. | High | Phase 1 | Dec 2025 | Asset Service, Auth Service | Edge cases: duplicate assets; effort: 40 person-days.
Cross-Platform SDK Integrator | SDK management: Sub-elements include Oculus/SteamVR/OpenXR config UI, version checking, dependency resolution, platform validation, and error logs. Workflow: Select SDK → configure → test. Metrics: <1min setup. | Unity XR Management; custom UI. | High | Phase 1 | Dec 2025 | Multi-Platform Build Tools | New; edge cases: SDK conflicts; effort: 25 person-days.
Multi-User App Collaboration | Co-develop apps: Sub-elements include avatar systems, spatial voice chat, real-time code sync (<50ms), conflict resolution UI, and session recordings. Workflow: Invite dev → edit app → merge changes. Metrics: 10+ users. | Photon Fusion; Agora voice; Unity Netcode. | Medium | Phase 2 | Jun 2026 | Collaboration Service | Edge cases: disconnects; effort: 40 person-days.
AI-Assisted App Development | Smart app tools: Sub-elements include procedural UI generation, code suggestion (e.g., input handlers), NLP prompts ('add menu'), platform-specific optimizations, and ethical filters. Workflow: Input prompt → generate code → refine. Metrics: <3s generation. | ML-Agents v2; Azure OpenAI via backend. | Medium | Phase 3 | Sep 2026 | AI Integration | Edge cases: biased code; effort: 50 person-days.
App Testing Suite | Test apps across platforms: Sub-elements include emulators (Quest/PC/Web), FPS/memory dashboards, automated input tests, crash reporting, and A/B testing. Workflow: Select platform → run test → export report. Metrics: <1min test. | Unity Device Simulator v3; custom profilers. | Medium | Phase 2 | Jun 2026 | Publishing Service | Edge cases: platform bugs; effort: 30 person-days.
App Accessibility | Inclusive apps: Sub-elements include color-blind modes, subtitle UI, scalable text, voice commands, haptic alternatives, and one-handed controls. Workflow: Enable setting → test app → save. Metrics: WCAG 2.2 AA. | Unity UI Toolkit; accessibility plugins. | Medium | Phase 3 | Sep 2026 | None | Test with diverse users; effort: 25 person-days.
Custom Scripting for Apps | C# for app logic: Sub-elements include VR code editor, app-specific templates (e.g., state triggers), breakpoints in VR, Git integration, and sandboxed execution. Workflow: Write code → debug → deploy. Metrics: <1s compile. | Visual Studio Code; VR UI overlays. | Medium | Phase 2 | Jun 2026 | Visual Scripting for Apps | Edge cases: runtime errors; effort: 30 person-days.
App Localization | Multi-language apps: Sub-elements include metadata translation, UI string keys, locale detection, RTL support, .po exports, and translation memory. Workflow: Set locale → update app → export. Metrics: <1s switch. | Unity Localization v1.4; VR UI. | Medium | Phase 3 | Sep 2026 | Custom Asset Library | 20 languages; edge cases: non-Latin; effort: 20 person-days.
App Performance Tools | App profiling: Sub-elements include FPS graphs, memory trackers, draw call analyzers, platform-specific metrics (ASW), and optimization suggestions. Workflow: Open profiler → analyze → optimize. Metrics: <1% overhead. | Unity Profiler; VR dashboards. | Medium | Phase 2 | Jun 2026 | App Testing Suite | Edge cases: VR stutter; effort: 25 person-days.
App State Management | App state handling: Sub-elements include save/load UI, cross-device sync, state serialization (JSON), rollback options, and error recovery. Workflow: Save state → sync → restore. Metrics: <1s save. | Custom state scripts; Unity Cloud. | Medium | Phase 2 | Jun 2026 | Scene Service | New; edge cases: partial saves; effort: 20 person-days.
AR App Support | Mobile AR apps: Sub-elements include ARKit/ARCore integration, plane detection, anchor placement, AR preview in VR, and export to AR formats. Workflow: Scan environment → build app → test. Metrics: <1s detection. | AR Foundation v5; XR Management. | Medium | Phase 2 | Jun 2026 | Asset Service | New; edge cases: lighting issues; effort: 30 person-days.
App Marketplace | App asset store: Sub-elements include upload moderation, ratings/reviews, search by tags, payment integration, and sales analytics. Workflow: Submit asset → review → publish. Metrics: <5s search. | Custom UI; Unity Asset Store API. | Medium | Phase 3 | Sep 2026 | Custom Asset Library | New; edge cases: fraud; effort: 40 person-days.
App Audio | 3D audio for apps: Sub-elements include spatial occlusion, reverb zones, MIDI for app soundtracks, volume curves, binaural support, and platform validation. Workflow: Place audio → configure → test. Metrics: <10ms latency. | Unity Audio Spatializer; FMOD v2. | Low | Phase 3 | Dec 2026 | Asset Service | Edge cases: echo; effort: 20 person-days.
App VFX | App effects: Sub-elements include particle systems for UI, shader effects (glow), wind/gravity for interactions, collision visuals, and preset library. Workflow: Create effect → adjust → save. Metrics: <5% GPU. | VFX Graph v14; Shader Graph. | Low | Phase 3 | Dec 2026 | App Rendering | Edge cases: overdraw; effort: 25 person-days.
App Feedback System | App feedback: Sub-elements include survey popups, error auto-reporting, feature voting, session replay, and analytics integration. Workflow: Report issue → track resolution. Metrics: <10s submission. | Unity Analytics; custom modals. | Low | Phase 3 | Dec 2026 | Analytics Service | GDPR-compliant; effort: 15 person-days.

## Frontend Web
Feature | Description | Implementation | Priority | Phase | Timeline | Dependencies | Notes
WebXR App Preview | Preview VR apps in browser: Sub-elements include WebXR session UI, immersive toggles (VR/2D), device permissions, 2D fallback (orbit controls), mobile AR previews, and platform validation. Workflow: Load app → enter WebXR → test. Metrics: <2s session. | WebXR API 1.1; Unity WebGL v2023; A-Frame. | High | Phase 1 | Dec 2025 | Publishing Service | Test Chrome/Safari; edge cases: permissions; effort: 25 person-days.
Browser Input Config | App input testing: Sub-elements include touch gestures (pinch-zoom), keyboard (WASD), mouse orbit, gamepad support, sensitivity sliders, and multi-platform mappings. Workflow: Configure input → test app → save. Metrics: <10ms latency. | Unity Input System; WebGL Pointer Lock; Hammer.js. | High | Phase 1 | Dec 2025 | Interactable System | Edge cases: iOS touch; effort: 20 person-days.
WebGL App Rendering | Render apps in browser: Sub-elements include dynamic resolution, texture mipmapping, shader fallbacks, loading bars, context loss recovery, and platform-specific optimizations. Workflow: Load app → adjust quality → test. Metrics: 60 FPS. | Unity URP v14; WebGL 2.0 scripts. | High | Phase 1 | Dec 2025 | App Rendering | Edge cases: context loss; effort: 25 person-days.
Web App Asset Support | App assets for WebXR: Sub-elements include GLTF validation, poly reduction (50k), streaming loads, format converters, cache management, and CORS handlers. Workflow: Upload asset → validate → use in app. Metrics: <3s load. | GLTFast v5; Web Workers. | High | Phase 1 | Dec 2025 | Asset Service | Edge cases: CORS; effort: 20 person-days.
Custom Asset Library (Web) | Web dashboard for app assets: Sub-elements include drag-drop uploads, WebGL previews, metadata editor, sharing links, collaborative editing, and Unity exports. Workflow: Upload → tag → share. Metrics: <3s preview. | React 18; Tailwind; WebGL shaders. | High | Phase 1 | Dec 2025 | Custom Asset Library (Backend) | Edge cases: large uploads; effort: 30 person-days.
Web App PWA | Installable app tester: Sub-elements include manifest configs, offline caching, service worker updates, push notifications, and install prompts. Workflow: Visit site → install → test offline. Metrics: <5MB cache. | Workbox; Unity WebGL PWA. | Medium | Phase 2 | Jun 2026 | Publishing Service | Edge cases: storage limits; effort: 15 person-days.
Web App Collaboration | Co-develop apps in browser: Sub-elements include cursor sharing, chat overlays, version locking, invite links, tab sync, and conflict UI. Workflow: Invite → edit app → merge. Metrics: <50ms sync. | WebSockets; Firebase; Yjs. | Medium | Phase 2 | Jun 2026 | Multi-User App Collaboration | Edge cases: tab crashes; effort: 30 person-days.
Web App Analytics | Track app usage: Sub-elements include event funnels, heatmaps, A/B test APIs, privacy opt-outs, CSV exports, and dashboards. Workflow: Track session → generate report. Metrics: <1s log. | Google Analytics 4; custom WebGL events. | Medium | Phase 2 | Jun 2026 | Analytics Service | Edge cases: ad blockers; effort: 15 person-days.
Web App Accessibility | Inclusive app testing: Sub-elements include ARIA labels, keyboard navigation, screen reader support, contrast checkers, and reduced motion. Workflow: Enable accessibility → test app. Metrics: WCAG 2.2 AA. | ARIA; WebGL polyfills. | Medium | Phase 3 | Sep 2026 | App Accessibility | Test with NVDA; effort: 20 person-days.
Web App Localization | Multi-language app testing: Sub-elements include locale detection, string loading, RTL layouts, currency/date formatting, and translation APIs. Workflow: Detect locale → load app UI. Metrics: <1s switch. | react-i18next; WebGL text. | Medium | Phase 3 | Sep 2026 | App Localization | 15 languages; effort: 15 person-days.
Web App Performance | Browser app profiling: Sub-elements include Lighthouse audits, network throttles, asset load timelines, error consoles, and optimization reports. Workflow: Run audit → optimize app. Metrics: <1% overhead. | Chrome DevTools; WebGL profilers. | Medium | Phase 2 | Jun 2026 | App Performance Tools | Edge cases: slow 3G; effort: 20 person-days.
Web AR App Support | AR app previews: Sub-elements include WebXR AR mode, plane detection, anchor UI, camera passthrough, and AR exports. Workflow: Scan room → test app. Metrics: <1s detection. | WebXR AR; 8th Wall. | Medium | Phase 2 | Jun 2026 | AR App Support | Edge cases: lighting; effort: 25 person-days.
Web App Notifications | Browser alerts for apps: Sub-elements include permission dialogs, customizable channels, vibration, badge updates, and offline queuing. Workflow: Subscribe → receive alert. Metrics: <2s delivery. | Web Push API; Service Workers. | Low | Phase 3 | Dec 2026 | Notification Service | Edge cases: denied permissions; effort: 10 person-days.
Web App Audio | App audio in browser: Sub-elements include WebAudio spatial nodes, context resumption, format fallbacks, volume normalization, and debug tools. Workflow: Load audio → test in app. Metrics: <10ms latency. | WebAudio API; Unity audio. | Low | Phase 3 | Dec 2026 | App Audio | Edge cases: muted tabs; effort: 15 person-days.

## Backend
Component | Description | Technologies | Priority | Phase | Timeline | Dependencies | Notes
API Gateway | App API routing: Sub-elements include rate limiting (100 req/s/user), versioning (v1/v2), audit logging, CORS for Unity/Web, health checks, and DDoS throttling. Endpoints: GET /health, POST /auth/token. Metrics: <100ms latency. | AWS API Gateway; Kong; OAuth2/JWT. | High | Phase 1 | Dec 2025 | None | 99.99% uptime; edge cases: traffic spikes; effort: 30 person-days.
Auth Service | App user management: Sub-elements include passwordless login, 2FA (TOTP), RBAC (developer/publisher), session revocation, audit trails, and SSO. Endpoints: POST /login, GET /users/me. Metrics: <500ms auth. | Firebase Auth; Keycloak; Postgres. | High | Phase 1 | Dec 2025 | None | GDPR export; edge cases: token theft; effort: 25 person-days.
Asset Service | App asset handling: Sub-elements include virus scanning, metadata indexing, thumbnail generation, deduplication, purge APIs, and CDN caching. Endpoints: POST /assets/upload, GET /assets/{id}. Metrics: <5s for 100MB. | S3; DynamoDB; FFmpeg; Cloudflare. | High | Phase 1 | Dec 2025 | API Gateway | 1GB+ files; edge cases: corrupt uploads; effort: 35 person-days.
App State Service | App state management: Sub-elements include JSON schema validation, version diffs, autosave (10s), rollback endpoints, USD export, and conflict detection. Endpoints: POST /states, GET /states/{id}/versions. Metrics: <1s save. | MongoDB 6; libgit2; Redis. | High | Phase 1 | Dec 2025 | API Gateway | 10MB+ states; edge cases: conflicts; effort: 30 person-days.
Collaboration Service | App co-development: Sub-elements include OT for code sync, presence indicators, chat persistence, bandwidth throttling, offline queues, and analytics. Endpoints: WS /collab/join. Metrics: <50ms sync. | Socket.io; Yjs; Redis Pub/Sub. | High | Phase 2 | Mar 2026 | App State Service | 50 users; edge cases: disconnects; effort: 40 person-days.
Database Layer | App data: Sub-elements include sharding, backups (daily), index optimization, Redis caching (1hr TTL), migrations, and HA configs. Schema: users, states, assets. Metrics: <10ms query. | Postgres 15; MongoDB 6; Redis 7. | High | Phase 1 | Dec 2025 | API Gateway | 99.9% uptime; edge cases: corruption; effort: 35 person-days.
Security & Compliance | App security: Sub-elements include AES-256 encryption, OWASP scans, GDPR/CCPA/HIPAA reports, WAF, audit logs, and anonymization. Endpoints: GET /compliance/report. Metrics: 0 vulnerabilities. | HTTPS/TLS 1.3; OWASP; CloudTrail. | High | Phase 1 | Dec 2025 | None | Quarterly pentests; edge cases: DDoS; effort: 30 person-days.
Custom Asset Library (Backend) | App asset storage: Sub-elements include ACLs, versioning, Elasticsearch indexing, auto-cleanup, bulk APIs, moderation, and audit logs. Endpoints: POST /library/upload, GET /library/search. Metrics: <500ms search. | S3; DynamoDB; Elasticsearch 8. | High | Phase 1 | Dec 2025 | Asset Service, Auth Service | 100TB scale; edge cases: conflicts; effort: 40 person-days.
Analytics Service | App usage tracking: Sub-elements include funnels (code-to-publish), cohort analysis, crash reports, dashboards, CSV exports, and GDPR opt-outs. Endpoints: POST /events, GET /reports. Metrics: <1s log. | Elasticsearch 8; Kafka; Kibana. | Medium | Phase 2 | Jun 2026 | API Gateway | Edge cases: large datasets; effort: 25 person-days.
Publishing Service | App deployment: Sub-elements include CI/CD pipelines (APK/WebGL/EXE), build queues, version tagging, rollback APIs, and platform analytics. Endpoints: POST /builds, GET /builds/{id}. Metrics: <5min build. | Jenkins; Unity Cloud Build; Docker. | Medium | Phase 2 | Jun 2026 | Asset Service | Edge cases: build failures; effort: 30 person-days.
AI Integration | AI for app dev: Sub-elements include prompt templating, rate limiting, asset/code caching, model selection (GPT-4o), billing trackers, and error handling. Endpoints: POST /ai/generate. Metrics: <3s response. | Azure OpenAI; Hugging Face; SQS. | Medium | Phase 3 | Sep 2026 | API Gateway | Edge cases: API downtime; effort: 40 person-days.
Scalability Layer | App scaling: Sub-elements include pod scaling, load balancer configs, stress tests (Locust), metrics (CPU/RAM), cost dashboards, and failover scripts. Metrics: 10k users. | Kubernetes 1.27; Prometheus; Grafana. | Medium | Phase 3 | Sep 2026 | API Gateway | Edge cases: spikes; effort: 35 person-days.
App State Recovery | App crash recovery: Sub-elements include autosave (10s), diff-based restore, cross-device sync, error logs, and recovery UI. Endpoints: POST /states/restore. Metrics: <5s restore. | MongoDB; Redis; S3. | Medium | Phase 2 | Jun 2026 | App State Service | Edge cases: partial saves; effort: 20 person-days.
Notification Service | App alerts: Sub-elements include template rendering, subscription UI, retry logic, analytics, SMS (Twilio), and spam filters. Endpoints: POST /notifications. Metrics: <2s delivery. | Firebase Cloud Messaging; AWS SES. | Low | Phase 3 | Dec 2026 | API Gateway | Edge cases: undeliverable; effort: 15 person-days.

## Product Launch Plan
Task | Description | Details | Priority | Phase | Timeline | Dependencies | Notes
Define App Developer Audience | Research VR app devs: Sub-elements include surveys (indie vs. enterprise needs), personas (game dev, training), competitor analysis (Unity, Godot), platform segmentation (Quest/WebXR), and use case validation (games, sims). Workflow: Survey → define segments. Metrics: 500+ responses. | SurveyMonkey; X polls; VR dev forums. | High | Phase 1 | Nov 2025 | None | Edge cases: niche apps; effort: 20 person-days.
Beta Testing for Apps | Test VR apps: Sub-elements include alpha (20 devs), public beta (200 devs), feedback forms, bug triage (Jira), A/B feature tests, and platform testing (Quest/PC/Web). Workflow: Deploy beta → iterate. Metrics: <5% crash rate. | TestFlight; Steam Beta; App Lab. | High | Phase 2 | Mar 2026 | App Testing Suite | Edge cases: low-end devices; effort: 40 person-days.
Monetization for App Devs | Revenue models: Sub-elements include freemium ($20/month pro), in-app asset purchases, enterprise licenses ($5k/year), affiliate links, and A/B pricing tests. Workflow: Set pricing → test → launch. Metrics: 10% conversion. | Stripe; PayPal; analytics. | High | Phase 2 | Mar 2026 | Auth Service | Edge cases: refunds; effort: 30 person-days.
App Compliance | Legal standards: Sub-elements include GDPR mapping, WCAG 2.2 audits, HIPAA for sims, CCPA compliance, privacy policies, and certifications. Workflow: Audit → remediate → certify. Metrics: 0 issues. | Legal reviews; Axe tool. | High | Phase 1 | Dec 2025 | Security & Compliance | Annual audits; effort: 25 person-days.
App Marketing | Promote app tool: Sub-elements include X/Reddit teasers, YouTube demos, VR streamer partnerships, email campaigns, virtual launch events, and $10k ad budget. Workflow: Plan → execute → track. Metrics: 1M impressions. | Hootsuite; Google Ads; Siggraph. | Medium | Phase 2 | Jun 2026 | Publishing Service | Edge cases: negative feedback; effort: 35 person-days.
Post-Launch App Support | Maintain app tool: Sub-elements include monthly patches, Discord forums, guides (video/text), churn analysis (5% target), feature voting, and roadmaps. Workflow: Monitor → patch → communicate. Metrics: <24hr response. | GitHub Issues; Zendesk. | Medium | Phase 3 | Dec 2026 | Analytics Service | Edge cases: breaking updates; effort: 30 person-days.
App Scalability Testing | Load test app tool: Sub-elements include spike tests (10k users), DB stress tests, failover drills, cost projections ($5k/month), and optimization scripts. Workflow: Simulate → optimize. Metrics: 99.99% uptime. | Locust; AWS; New Relic. | Medium | Phase 2 | Jun 2026 | Scalability Layer | Edge cases: outages; effort: 25 person-days.

## Completed Features
Sno | Feature | Description | Team | Status | Priority | Phase | Timeline | Dependencies | Notes
1 | App Hierarchy | Manage app objects: Sub-elements include tree view (expand/collapse), search by name/type, drag-reorder, multi-select delete, and linking for app logic. Workflow: Open hierarchy → reorder → save. Metrics: <100ms refresh. | XR | Completed | High | Phase 1 | Aug 2025 | None | Integrate with Custom Asset Library; effort: 10 person-days.
2 | App Scene | App logic container: Sub-elements include scene loading, multi-scene support, layer management, prefab instantiation, and save/load UI. Workflow: Create scene → add logic → save. Metrics: <2s load. | XR | Completed | High | Phase 1 | Aug 2025 | None | Add multi-user sync; effort: 15 person-days.
3 | Move App Object | Move app objects: Sub-elements include gizmo controls, numeric input, snap-to-grid, multi-object move, and undo. Workflow: Select → move → confirm. Metrics: <10ms response. | XR | Completed | High | Phase 1 | Aug 2025 | App Scene | Add VR gestures; effort: 5 person-days.
44 | Reset App Object | Reset app object transforms: Sub-elements include one-click zeroing, batch reset, undo, confirmation dialogs, and gizmo visuals. Workflow: Select → reset → confirm. Metrics: <100ms action. | XR | Completed | Medium | Phase 1 | Aug 2025 | App Scene | Add VR button; effort: 5 person-days.

## Sub-Features Breakdown
Parent Feature | Sub-Feature | Description | Priority | Phase | Timeline | Dependencies | Notes
App Logic Editor | State Machine UI | Drag-drop state creation; supports transitions, triggers, and platform-specific states. Metrics: <1s transition. | High | Phase 1 | Dec 2025 | Visual Scripting for Apps | Edge cases: state conflicts; effort: 10 person-days.
App Logic Editor | Event Triggers | UI for onInput/onStateChange; supports custom events, VR previews. Metrics: <10ms trigger. | High | Phase 1 | Dec 2025 | Interactable System | Edge cases: event loops; effort: 8 person-days.
Multi-Platform Build Tools | SDK Injection | Auto-inject Oculus/SteamVR SDKs; includes version checks, dependency resolution. Metrics: <1min setup. | High | Phase 1 | Dec 2025 | Cross-Platform SDK Integrator | Edge cases: version mismatches; effort: 10 person-days.
Multi-Platform Build Tools | Build Validation | Validate app for platform specs (e.g., Quest poly limits); includes error logs. Metrics: <30s validation. | High | Phase 1 | Dec 2025 | Publishing Service | Edge cases: invalid configs; effort: 8 person-days.
Custom Asset Library | Asset Tagging | AI-suggested tags for app assets; supports hierarchies, search facets. Metrics: <500ms search. | High | Phase 1 | Dec 2025 | AI Integration | Edge cases: duplicates; effort: 10 person-days.
Custom Asset Library | Sharing Permissions | ACLs for app assets; includes invite links, role-based access. Metrics: <200ms check. | High | Phase 1 | Dec 2025 | Auth Service | Edge cases: revoked access; effort: 10 person-days.
WebXR App Preview | Session Initiation | Enter WebXR for app testing; includes device detection, error UI. Metrics: <2s start. | High | Phase 1 | Dec 2025 | None | Edge cases: unsupported browsers; effort: 5 person-days.
WebXR App Preview | Immersive Toggles | Switch VR/2D for app testing; includes UI animations. Metrics: <1s toggle. | High | Phase 1 | Dec 2025 | Browser Input Config | Edge cases: mode conflicts; effort: 5 person-days.
Custom Asset Library | Versioning | Track asset versions; supports diffs, rollback, comments. Metrics: <1s diff load. | Medium | Phase 2 | Mar 2026 | App State Service | Edge cases: conflicts; effort: 8 person-days.
Custom Asset Library | Moderation Tools | Flag/review app assets; includes admin UI, AI flagging. Metrics: <1s processing. | Medium | Phase 2 | Mar 2026 | AI Integration | Edge cases: false positives; effort: 7 person-days.